## Sheet1
General Note:
1. Please enter all values in Millions
2. Incorporate all expeditures and update accordingly as and when the payments are verified from our side
3. The progress will be monitored through this forum at various frequencies and reviewed accordingly your IWP
4. Please create sub-activites as shown in the Core Area Re-development activities if required
5. DO NOT ADD OR DELETE ANY ACTIVITES
Activities under IDD for the fiscal year 2021-2022
SL. No | Activities | Approved Budget (Nu) | Source of Fund | Progress 20% | [6 empty] | Progress 80%
|  |  |  | Estimated Amount or TS Amount (Nu.) | Date of TS | Date Of AS & FS | NIT date | Letter of Intent Date | Letter of Acceptance | Work Order | Date for Commencement | Expected date of completion | Name of Contractor | Contract Amount (Nu) | Expenditure during 2020-21 FY(Nu) | Expenditure during 2021-22 FY(Nu) | Budget Balance(Nu) | Total Progress Achieved (%) | Remarks | Remarks from Chief | Your comments or clarifications required
1 | Construction of G+1 integrated vegetable shed in Gelephu Town (SDP II) 90% completed by June 2022. | 28.87 | SDP | 44.414 | 2020-07-07 | 2020-10-07 | 21/07/2020 | 18/12/2020 | 2021-06-01 | 15/01/2021 | 2021-01-02 | 31/01/2022 |  | 44.414 | 14.92 |  | 28.87(Approved budget-Expenditure) | 25%(contract amount/Expeniture)*100 | Progress as on 19-8-2021
2 | Construction of 4 lane 3D Arch bridge(60m) over small Aipoli under Development of the urban road in LAP VI (SDP II) 65% completed by June 2022. | 120 | SDP | 150.24 | GT/IDD-07/2020-2021/522 dated 30TH December 2020 | GT/Acct-09/2019-2020/2745 dated 30/5/2020, |  |  |  | GT/IDD-15/2020/2021/1521 dated 18th December 2020, | 2021-01-01 | 30/6/2022 | CDCL | 151.313 | 30.1512 | 37.689 | 82.311 | 23.67 | 3rd RAB vlaimed submited to account, no fund avaliable lo on 13/8/2021
3 | Construction of public toilet at Border Check Point | 1.9 | RGoB | - | - | - | - | - | - | - |  |  |  | - |  |  | 1.9 | - |  | Not yet updated | Design not yet received from DRD. Learned that the Architect did discuss the matter with Chief
4 | Construction/Maintenance of sports infrastructure facilities | 2 | RGoB | [13 empty] | 2 |  |  | Not yet updated
5 | Construction/Maintenance of Crematoriums | 2.53 | RGoB | [13 empty] | 2.53 |  |  | It is not neccessary to revise the estimates based on approved budget but may be revised should there be important activities left out initially | If we can consult the concerned person to know if we have left out the activities which we might have overlook. The works not included in the estimates which actually required to execute during the implementation, the contractor are reluctant to do the works and usually claim higher rates la | Please program one appropriate day for your visit and revise the estimates at the earliest.
6 | Construction of 12 units additonal classrooms at GMSS | 7.87 | RGoB | 19.67 | 19/12/2019 | 19/12/2019 | 2020-07-01 | 2020-05-03 | 18/3/2020 | 2020-01-04 | 2020-06-04 | 15/11/2020 |  | 17.87 | 2.34 | 1.462 | 6.408 | 20%
7 | Construction of Vegetable shed in Rabdeyling | 1 | RGoB | 1.05 | 21/4/2021 | 22/4/2021 | 2021-04-05 | 16/6/2021 | 18/6/2021 | 2021-12-07 | 26/7/2021 | 25/12/2021 |  | 0.871 |  | 0.239 | 0.761 | 10%
8 | Construction of Common Service Duct at Urban Corrodor complete (350 Meter) | 6 | SDP | 10.31 | 27/03/2021 | Approved Note Sheet No.GT/IDD-10/2020-2021/2658 | No.GT/IDD-10/2020-2021/2658 |  | GT/IDD-15/2020-2021/2657 | GT/IDD-15/2020-2021/2684 | 2021-01-04 | 15/08/2021 | M/S. Sonam Rinchen Construction Pvt. Ltd, CDB No.1488. Gelephu. | 9.73 | 6.5 | 6.5 | -0.5 | 65% | This activites is under Development of Urban Corridor (3 nos of culverts and Common Duct of 350m) total SDP Budget is 50M. | Its SDP activity under FIC 5356 - Development of Urban Corridor in LAP VI (Permanet works -drains and culverts), Please update expenditures as on date
9 | 30% of Core Area redeveloped | 34.24 | RGoB | [10 empty] | 0 | 0 | 0 | 34.24 |  |  | Please update activities as per the format
9.1
9.2 .........
9.3...........
9.4
10 | Regular maintenance of Urban Roads traffic sinage and footpath completed | 12.81 | RGoB | 7.6 | GT/IDD-15/2020-2021/853 | GT/ACCt-09/2020-2021/1447 | Tender ID: 6498 through egp | GT/IDD-15/2020-2021/1257 | GT/IDD-15/2020-2021/1366 | GT/IDD-15/2020-2021/1435 | 15/12/2020 | 2021-10-07 | M/S. Zhenrdup Construction Gelephu. | 8.64 | 8.5 | 10.2 | 2.61 | Completed 100% | FInal bill for zhendup completed and delaunching 0.2m | Please update with exact expenditures
11 | Regular maintenance of Urban Roads and footpath completed | 13.66 | RGoB | [13 empty] | 13.66 |  | Estimate under progress | Please expedite
12 | Construction of water supply network in LAP IV (SDP II) | 11.78 | SDP | [13 empty] | 11.78 |  |  | Not yet updated
13 | Construction of Steel water tank at Namkhaling | 3.5 | RGoB | [13 empty] | 3.5 |  |  | Not yet updated
14 | Regular maintenance of water supply of Gelephu Throm results positive efficiency with 5% | 8.25 | RGoB | [12 empty] | 2.3 | 5.95 |  | Supply order placed for major essential plumbing items required for maintenance | Muster roll payment and plumbing items purchased till 23..08.2021.
15 | Improvement of infiltration Gallery at Mouchu Treatement Plant | 16.82 | RGoB | [13 empty] | 16.82 |  |  | Not yet updated
16 | Renovation and maintenance of main water transmission line from intake to WTP at Pelrithang | 5.34 | RGoB | 5.115 | 17/08/2021 | [11 empty] | 5.34
17 | Installation of LED streetlights at LAP II and IV (70 Nos.) | 2.93 | RGoB | [13 empty] | 2.93 |  |  | Not yet updated
18 | Operation and Maintenance of Streetlights | 5.56 | RGoB | [13 empty] | 5.56 |  |  | Not yet updated
19 | Construction of flood protection wall at Mouchu | 10 | RGoB | 8.33 | 19/08/2021 | 19/08/2021 | [10 empty] | 10
20 | Maintenance of office parking and compond fencing | 3.8 | RGoB | 4.15 | 19/01/2021 | 26/01/2021 | Approved direct award on 8/02/2021 |  | 17/02/2021 | 24/02/2021 | 24/02/2021 | 24/11/2021 |  | 4.15 | 1.37 |  | 3.8 | 35%
21 | Infrastructure development related to COVID-19 pandemic | 2 | RGoB |  | 2021-01-07 | 30/7/2021 | departmentally executed | [8 empty] | 1.721 | 0.279 | 100% | Progress as on 19-8-2021, Approcah road completed, {portable cabin shifted to site, Estimate for Labour camp completed within July 2021 | Please update with exact expenditures as on date
22 | Construction of footpath and biking trail at City Central Park | 10 | Revenue | [13 empty] | 10 |  | Estimate under progress | Please expedite estimation
|  | 310.86 |  | 250.879 | [9 empty] | 236.983 | 63.781 | 60.111 | 250.749